## Slide 1: Texas State University – Capital Projects Administration Quarterly Meeting
July 7, 2023

## Slide 2: Ballpark Clubhouse
Budget: $9.9M
Status: Architect negotiations for Phase I work (Pitching Lab and batting cages).
Est. Construction Start: TBD
Est. Construction Completion: January 2025
Scope: Project includes hospitality suite,
new box seating, players lounge, batting
cages, pitching lab and new softball players
lounge.

## Slide 3: Music Building
Budget: $90.0M (CIP)
Status: Pre-planning/Fundraising
Estimated Construction Start: TBD
Estimated Construction Completion: TBD
Scope: New 85,000 GSF music center will include classroom and rehearsal space, located next to the Performing Arts Center.

## Slide 4: STEM Classroom Building
Budget: $137.4M
Status: Project ‘Kick-Off’ with Architect / CM@R selection pending
Est. Construction Start: June 2024
Est. Construction Completion: July 2026
Scope: New 154,000 academic/lab building will house the Departments of Mathematics and Computer Science on the San Marcos Campus.

## Slide 5: Esperanza Hall
Budget: $52.4M
Status: A/E Negotiations Pending / CM@R Solicitation Cancelled. Final draft of Space Utilization Survey is under review.
Estimated Construction Start: TBD
Estimated Construction Completion: TBD
Scope: New 81,651 sf academic building to house classrooms,
labs, and offices to support the College of Health Professions,
on the Round Rock Campus.

## Slide 6: JC Kellam (JCK) Administration Building Reconfiguration
Budget: $7.9M
Status: 26% Complete. Demolition of interior is complete. Installation of metal framing, drywall & MEP rough-in on-going
Construction Start: March 2023
Estimated Construction Completion: September 2023
Scope: This project will convert the eleventh-floor into event, hospitality and meeting space for various functions, and replace existing roof.

## Slide 7: JC Kellam- 11th Floor Reconfiguration

## Slide 8: JC Kellam (JCK) Lobby/Parking Modifications
Budget: $4.0M
Status: Construction Documents
Construction Start: August 2023
Estimated Construction Completion: December 2023
Scope: This project will construct a new covered entry Lobby and reconfigure the parking to allow pick-up / drop-off in front of the building.

## Slide 9: Bobcat Stadium End Zone Complex Expansion
Budget: $37.0M (CIP)
Status: Construction Documents – CMR finalizing GMP for project.
Estimated Construction Start: July 2023
Estimated Construction Completion: October 2024
Scope: New weight and athletic training room, expand the current locker rooms, repurpose the existing weight room space for position meeting rooms, and create additional hospitality spaces.

## Slide 10: Rooftop Terrace

## Slide 11: Hilltop Housing Complex
Budget: $125.1M
Status: Construction – 30%
Construction Start: May 2022
Estimated Construction Completion: June 2024
Scope: Construction of two, seven-story structures comprised of 241,000 sf, and accommodating 1006 beds.
North Tower – Alamito Hall
South Tower – Cibolo Hall

## Slide 12: Hilltop Housing Complex

## Slide 13: Hilltop Housing Complex

## Slide 15: James Street Housing
Budget: $124M
Status: Schematic Design
Est. Construction Start: November 2023
Est. Construction Completion: July 2025
Scope: Construction of a seven-story residential structure with central community area, comprised of 221,240sf, and accommodating 950 beds.

## Slide 16: McCoy Student Success Center
Budget: $1.0M (CIP)
Status: Construction – 100%
Construction Start: March 2023
Estimated Construction Completion: June 2023
Scope: This project renovates Classroom 111 and Student Organization Room 110 into the new Student Success Center. Center will house offices, conference room, interview room and lobby.
Drywall installation is underway.

## Slide 17: McCoy Student Success Center

## Slide 18: McCoy Student Success Center

## Slide 19: East-West Mall Connection
Budget: $1.6M
Status: Site utility installation & site grading
Construction Start: May 2023
Estimated Construction Completion: December 2023
Scope: Construct new paved pedestrian mall from RF Mitte to Academy Street. New pedestrian mall to include landscaping, seating, power pedestals and lighting.

## Slide 20: East-West Mall Connection

## Slide 21: East – West Mall Connection

## Slide 22: Campus Master Plan
Status: Contract is in place. Establishing Committees.
Schedule:
Begin Master Plan Process – 06/2023
Final Draft (Review) – 09/2024
TSUS Planning & Construction Comm –10/2024
Approval by BOR – 11/21/2024

## Slide 23: Capital Projects Quarterly Meeting